## Technical RAID Log
ID | Type | Description | Impact | Likelihood | Mitigation / Response | Owner | Status
R1 | Risk | Severe class imbalance (0.172% fraud) causes the model to default toward predicting 'not fraud'. | High | High | Apply class weighting and resampling (SMOTE/undersampling); evaluate with PR-AUC and recall, not accuracy. | Data Science Lead | Open
R2 | Risk | SHAP explanations may not be intuitive to non-technical fraud analysts, undermining adoption. | Medium | Medium | Pilot dashboard with 2-3 analysts before full rollout; iterate on explanation presentation based on feedback. | Data Science Lead | Open
R3 | Risk | Fairness audit may reveal disparate false-positive rates across customer segments. | High | Medium | Run Fairlearn/SHAP fairness audit before deployment; apply post-processing equalized-odds adjustment if disparity exceeds threshold. | Ethics Committee | Open
A1 | Assumption | Historical transaction data is complete enough to represent normal vs. fraudulent patterns. | High | - | Validate via exploratory data analysis in Module 3; flag if key segments are underrepresented. | Data Engineer | Open
A2 | Assumption | A production institution would grant API-level access to core banking transaction data. | Medium | - | Confirm data access scope with Head of Compliance before architecture finalization. | Project Lead | Open
I1 | Issue | Public dataset (ULB Credit Card Fraud) lacks demographic/regional fields needed for full fairness auditing. | Medium | - | Document this limitation explicitly; propose demographic proxy analysis (e.g., BISG-style) if deployed on real data. | Data Science Lead | Open
D1 | Dependency | Modeling work (Module 3) depends on this architecture and repository structure being finalized. | High | - | Freeze repository structure and environment.yml before Module 3 begins. | Project Lead | Open
D2 | Dependency | Fairness and explainability audit (Section 6) depends on a trained model existing first. | Medium | - | Sequence fairness audit as a Sprint 3 deliverable, after initial model training in Sprint 2. | Data Science Lead | Open
D3 | Dependency | NDPA compliance checklist finalization depends on confirming whether this is treated as a live deployment plan or an academic simulation. | Medium | - | Clarify scope with instructor; document assumption in Section 6 regardless. | Project Lead | Open